## Proposal
| May |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
Week Nr. | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Research
Writing
Proposal
Ethics
Malawi
Introduction
Presentation
Literature Review
Preparation Implementation
Field Study Data Collection
North
South
Central
Contacting Officials
Data Analysis
Methods
Results, Conclusion, Abstract
Submission
Ethics Feedback

## Ethics
| May |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
Week Nr. | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Research
Writing
Proposal
Ethics
Malawi
Introduction
Presentation
Literature Review
Questionnaire Preparation
Field Study Data Collection
North
South
Central
Contacting Officials
Data Analysis
Methods
Results, Conclusion, Abstract
Submission
Ethics Feedback
Writing
Piloting

## DHO
Month | September | [8 empty] | September | [9 empty] | October
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 26 | 27 | 28 | 29 | 30
Research
Thyolo Data Collection
Thyolo
Presentations
other Districts